## Cover
B2B DATA ENGINEERING PLATFORM
Test Case Register (annex to Test Document)
Version | 1.1
Prepared by | Syed Kazim Raza
Reviewed by | [Team Lead]
Date | 30/09/2026
Document ID | B2B-DEP-08b
How to use | One row per test case. Expected result for SQL checks is normally '0 rows'. Status: Pass / Fail / Blocked / Not Run.

## Summary
Level | Planned | Executed | Passed | Failed | Blocked | Pass %
Unit
Integration
KPI Validation
Total

## Unit_Tests
Test ID | Level | Layer | Object Under Test | Test Type | Description | Test Script / File | Expected Result | Actual Result | Status | Executed On | Evidence | Defect ID
UT-001 | Unit | Intermediate | intermediate.categories | Completeness | Null category ids | postgresql/intermediate/tests/Test_categories.sql (TEST 1) | 0 rows | 0 rows | Pass | 30/09/2026
UT-002 | Unit | Intermediate | intermediate.categories | Uniqueness | Duplicate category ids | postgresql/intermediate/tests/Test_categories.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026
UT-003 | Unit | Intermediate | intermediate.categories | Uniqueness | Duplicate category names | postgresql/intermediate/tests/Test_categories.sql (TEST 3) | 0 rows | 0 rows | Pass | 30/09/2026
UT-004 | Unit | Intermediate | intermediate.categories | Completeness | Required text fields | postgresql/intermediate/tests/Test_categories.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026
UT-005 | Unit | Intermediate | intermediate.categories | Completeness | Required timestamps | postgresql/intermediate/tests/Test_categories.sql (TEST 5) | 0 rows | 0 rows | Pass | 30/09/2026
UT-006 | Unit | Intermediate | intermediate.customers | Completeness | Null customer ids | postgresql/intermediate/tests/Test_customers.sql (TEST 1) | 0 rows | 0 rows | Pass | 30/09/2026
UT-007 | Unit | Intermediate | intermediate.customers | Uniqueness | Duplicate customer ids and email | postgresql/intermediate/tests/Test_customers.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026
UT-008 | Unit | Intermediate | intermediate.customers | Completeness | Required fields | postgresql/intermediate/tests/Test_customers.sql (TEST 3) | 0 rows | 0 rows | Pass | 30/09/2026
UT-009 | Unit | Intermediate | intermediate.customers | Domain / allowed values | Gender validation | postgresql/intermediate/tests/Test_customers.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026
UT-010 | Unit | Intermediate | intermediate.customers | Consistency | Timestamp validation | postgresql/intermediate/tests/Test_customers.sql (TEST 5) | 0 rows | 0 rows | Pass | 30/09/2026
UT-011 | Unit | Intermediate | intermediate.customers | Business rule | Customer business rules | postgresql/intermediate/tests/Test_customers.sql (TEST 6) | 0 rows | 0 rows | Pass | 30/09/2026
UT-012 | Unit | Intermediate | intermediate.order_items | Uniqueness | Duplicate order item ids | postgresql/intermediate/tests/Test_order_items.sql (TEST 1) | 0 rows | 0 rows | Pass | 30/09/2026
UT-013 | Unit | Intermediate | intermediate.order_items | Completeness | Required fields | postgresql/intermediate/tests/Test_order_items.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026
UT-014 | Unit | Intermediate | intermediate.order_items | Business rule | Quantity validation | postgresql/intermediate/tests/Test_order_items.sql (TEST 3) | 0 rows | 0 rows | Pass | 30/09/2026
UT-015 | Unit | Intermediate | intermediate.order_items | Business rule | Price validation | postgresql/intermediate/tests/Test_order_items.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026
UT-016 | Unit | Intermediate | intermediate.order_items | Reconciliation | Line total validation | postgresql/intermediate/tests/Test_order_items.sql (TEST 5) | 0 rows | 0 rows | Pass | 30/09/2026
UT-017 | Unit | Intermediate | intermediate.order_items | Consistency | Timestamp validation | postgresql/intermediate/tests/Test_order_items.sql (TEST 6) | 0 rows | 0 rows | Pass | 30/09/2026
UT-018 | Unit | Intermediate | intermediate.order_items | Business rule | Order business rule | postgresql/intermediate/tests/Test_order_items.sql (TEST 7) | 0 rows | 0 rows | Pass | 30/09/2026
UT-019 | Unit | Intermediate | intermediate.order_items | Business rule | Supplier product mapping | postgresql/intermediate/tests/Test_order_items.sql (TEST 8) | 0 rows | 0 rows | Pass | 30/09/2026
UT-020 | Unit | Intermediate | intermediate.order_items | Reconciliation | Order total reconciliation | postgresql/intermediate/tests/Test_order_items.sql (TEST 9) | 0 rows | 0 rows | Pass | 30/09/2026
UT-021 | Unit | Intermediate | intermediate.orders | Uniqueness | Duplicate order ids | postgresql/intermediate/tests/Test_orders.sql (TEST 1) | 0 rows | 0 rows | Pass | 30/09/2026 | S7
UT-022 | Unit | Intermediate | intermediate.orders | Completeness | Required fields | postgresql/intermediate/tests/Test_orders.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026 | S7
UT-023 | Unit | Intermediate | intermediate.orders | Domain / allowed values | Order status validation | postgresql/intermediate/tests/Test_orders.sql (TEST 3) | 0 rows | 0 rows | Pass | 30/09/2026 | S7
UT-024 | Unit | Intermediate | intermediate.orders | Domain / allowed values | Payment status validation | postgresql/intermediate/tests/Test_orders.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026 | S7
UT-025 | Unit | Intermediate | intermediate.orders | Reconciliation | Order total validation | postgresql/intermediate/tests/Test_orders.sql (TEST 5) | 0 rows | 0 rows | Pass | 30/09/2026 | S7
UT-026 | Unit | Intermediate | intermediate.orders | Consistency | Timestamp validation | postgresql/intermediate/tests/Test_orders.sql (TEST 6) | 0 rows | 0 rows | Pass | 30/09/2026 | S7
UT-027 | Unit | Intermediate | intermediate.orders | Business rule | Customer business rules | postgresql/intermediate/tests/Test_orders.sql (TEST 7) | 0 rows | 0 rows | Pass | 30/09/2026 | S7
UT-028 | Unit | Intermediate | intermediate.orders | Business rule | Company business rule | postgresql/intermediate/tests/Test_orders.sql (TEST 8) | 0 rows | 0 rows | Pass | 30/09/2026 | S7
UT-029 | Unit | Intermediate | intermediate.orders | Business rule | Marketing lead relationship | postgresql/intermediate/tests/Test_orders.sql (TEST 9) | 0 rows | 0 rows | Pass | 30/09/2026 | S7
UT-030 | Unit | Intermediate | intermediate.orders | Business rule | Order item relationship | postgresql/intermediate/tests/Test_orders.sql (TEST 10) | 0 rows | 0 rows | Pass | 30/09/2026 | S7
UT-031 | Unit | Intermediate | intermediate.orders | Reconciliation | Order total reconciliation | postgresql/intermediate/tests/Test_orders.sql (TEST 11) | 0 rows | 0 rows | Pass | 30/09/2026 | S7
UT-032 | Unit | Intermediate | intermediate.products | Completeness | Null product ids | postgresql/intermediate/tests/Test_products.sql (TEST 1) | 0 rows | 0 rows | Pass | 30/09/2026
UT-033 | Unit | Intermediate | intermediate.products | Uniqueness | Duplicate product ids | postgresql/intermediate/tests/Test_products.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026
UT-034 | Unit | Intermediate | intermediate.products | Uniqueness | Duplicate skus | postgresql/intermediate/tests/Test_products.sql (TEST 3) | 0 rows | 0 rows | Pass | 30/09/2026
UT-035 | Unit | Intermediate | intermediate.products | Completeness | Required fields | postgresql/intermediate/tests/Test_products.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026
UT-036 | Unit | Intermediate | intermediate.products | Referential integrity | Product → category | postgresql/intermediate/tests/Test_products.sql (TEST 5) | 0 rows | 0 rows | Pass | 30/09/2026
UT-037 | Unit | Intermediate | intermediate.products | Business rule | Price validation | postgresql/intermediate/tests/Test_products.sql (TEST 6) | 0 rows | 0 rows | Pass | 30/09/2026
UT-038 | Unit | Intermediate | intermediate.products | Consistency | Timestamp validation | postgresql/intermediate/tests/Test_products.sql (TEST 7) | 0 rows | 0 rows | Pass | 30/09/2026
UT-039 | Unit | Intermediate | intermediate.suppliers | Completeness | Null supplier ids | postgresql/intermediate/tests/Test_suppliers.sql (TEST 1) | 0 rows | 0 rows | Pass | 30/09/2026
UT-040 | Unit | Intermediate | intermediate.suppliers | Uniqueness | Duplicate supplier ids | postgresql/intermediate/tests/Test_suppliers.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026
UT-041 | Unit | Intermediate | intermediate.suppliers | Uniqueness | Duplicate emails | postgresql/intermediate/tests/Test_suppliers.sql (TEST 3) | 0 rows | 0 rows | Pass | 30/09/2026
UT-042 | Unit | Intermediate | intermediate.suppliers | Completeness | Required fields | postgresql/intermediate/tests/Test_suppliers.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026
UT-043 | Unit | Intermediate | intermediate.suppliers | Referential integrity | Supplier → company | postgresql/intermediate/tests/Test_suppliers.sql (TEST 5) | 0 rows | 0 rows | Pass | 30/09/2026
UT-044 | Unit | Intermediate | intermediate.suppliers | Referential integrity | Orphaned company references | postgresql/intermediate/tests/Test_suppliers.sql (TEST 6) | 0 rows | 0 rows | Pass | 30/09/2026
UT-045 | Unit | Intermediate | intermediate.suppliers | Consistency | Timestamp validation | postgresql/intermediate/tests/Test_suppliers.sql (TEST 7) | 0 rows | 0 rows | Pass | 30/09/2026
UT-046 | Unit | Intermediate | intermediate.web_logs | Uniqueness | Duplicate log ids | postgresql/intermediate/tests/Test_web_logs.sql (TEST 1) | 0 rows | 0 rows | Pass | 30/09/2026
UT-047 | Unit | Intermediate | intermediate.web_logs | Completeness | Required fields | postgresql/intermediate/tests/Test_web_logs.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026
UT-048 | Unit | Intermediate | intermediate.web_logs | Domain / allowed values | Http status code validation | postgresql/intermediate/tests/Test_web_logs.sql (TEST 3) | 0 rows | 0 rows | Pass | 30/09/2026
UT-049 | Unit | Intermediate | intermediate.web_logs | Business rule | Bytes sent validation | postgresql/intermediate/tests/Test_web_logs.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026
UT-050 | Unit | Intermediate | intermediate.web_logs | Domain / allowed values | Http method validation | postgresql/intermediate/tests/Test_web_logs.sql (TEST 5) | 0 rows | 0 rows | Pass | 30/09/2026
UT-051 | Unit | Intermediate | intermediate.companies | Completeness | Null company ids | postgresql/intermediate/tests/Tests_companies.sql (TEST 1) | 0 rows | 0 rows | Pass | 30/09/2026
UT-052 | Unit | Intermediate | intermediate.companies | Uniqueness | Duplicate company ids | postgresql/intermediate/tests/Tests_companies.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026
UT-053 | Unit | Intermediate | intermediate.companies | Uniqueness | Duplicate company name / tax id | postgresql/intermediate/tests/Tests_companies.sql (TEST 3) | 0 rows | 0 rows | Pass | 30/09/2026
UT-054 | Unit | Intermediate | intermediate.companies | Completeness | Required text fields | postgresql/intermediate/tests/Tests_companies.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026
UT-055 | Unit | Intermediate | intermediate.companies | Range | Rating | postgresql/intermediate/tests/Tests_companies.sql (TEST 5) | 0 rows | 0 rows | Pass | 30/09/2026
UT-056 | Unit | Intermediate | intermediate.companies | Completeness | Required timestamps | postgresql/intermediate/tests/Tests_companies.sql (TEST 6) | 0 rows | 0 rows | Pass | 30/09/2026
UT-057 | Unit | Intermediate | intermediate.companies | Business rule | Empty / whitespace values | postgresql/intermediate/tests/Tests_companies.sql (TEST 7) | 0 rows | 0 rows | Pass | 30/09/2026
UT-058 | Unit | Intermediate | intermediate.companies | Profiling (informational) | Country distribution | postgresql/intermediate/tests/Tests_companies.sql (TEST 8) | Informational distribution | 3 countries: US 1,719 / UK 518 / AU 263 | Pass | 30/09/2026
UT-059 | Unit | Intermediate | intermediate.companies | Profiling (informational) | Country / city combinations | postgresql/intermediate/tests/Tests_companies.sql (TEST 9) | Informational distribution | 11 country/city combinations | Pass | 30/09/2026
UT-060 | Unit | Intermediate | intermediate.companies | Business rule | Business location validation | postgresql/intermediate/tests/Tests_companies.sql (TEST 10) | 0 rows | 0 rows | Pass | 30/09/2026
UT-061 | Unit | Intermediate | intermediate.companies | Domain / allowed values | Company type | postgresql/intermediate/tests/Tests_companies.sql (TEST 11) | All quality counters = 0 | 2,500 companies, 2,500 unique ids, all missing/invalid counters 0 | Pass | 30/09/2026
UT-062 | Unit | Intermediate | intermediate.companies | Business rule | Overall data quality summary | postgresql/intermediate/tests/Tests_companies.sql (TEST 11) | All quality counters = 0 | 2,500 companies, 2,500 unique ids, all missing/invalid counters 0 | Pass | 30/09/2026
UT-063 | Unit | Intermediate | intermediate.supplier_product_mapping | Completeness | Null primary ids | postgresql/intermediate/tests/Tests_supplier_product_mapping.sql (TEST 1) | 0 rows | 0 rows | Pass | 30/09/2026
UT-064 | Unit | Intermediate | intermediate.supplier_product_mapping | Uniqueness | Duplicate supplier_product ids | postgresql/intermediate/tests/Tests_supplier_product_mapping.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026
UT-065 | Unit | Intermediate | intermediate.supplier_product_mapping | Uniqueness | Duplicate supplier / product combinations | postgresql/intermediate/tests/Tests_supplier_product_mapping.sql (TEST 3) | 0 rows | 0 rows | Pass | 30/09/2026
UT-066 | Unit | Intermediate | intermediate.supplier_product_mapping | Completeness | Required fields | postgresql/intermediate/tests/Tests_supplier_product_mapping.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026
UT-067 | Unit | Intermediate | intermediate.supplier_product_mapping | Business rule | Supplier reference | postgresql/intermediate/tests/Tests_supplier_product_mapping.sql (TEST 5) | 0 rows | 0 rows | Pass | 30/09/2026
UT-068 | Unit | Intermediate | intermediate.supplier_product_mapping | Business rule | Product reference | postgresql/intermediate/tests/Tests_supplier_product_mapping.sql (TEST 6) | 0 rows | 0 rows | Pass | 30/09/2026
UT-069 | Unit | Intermediate | intermediate.supplier_product_mapping | Business rule | Price / lead time validation | postgresql/intermediate/tests/Tests_supplier_product_mapping.sql (TEST 7) | 0 rows | 0 rows | Pass | 30/09/2026
UT-070 | Unit | Intermediate | intermediate.supplier_product_mapping | Consistency | Timestamp validation | postgresql/intermediate/tests/Tests_supplier_product_mapping.sql (TEST 8) | 0 rows | 0 rows | Pass | 30/09/2026
UT-071 | Unit | Warehouse | warehouse.dim_companies | Reconciliation | Baseline row counts | postgresql/warehouse/tests/dim_companies_tests.sql (TEST 1) | current rows = distinct companies | 2,505 rows, 2,500 companies, 2,500 current, 5 historical | Pass | 30/09/2026 | S10
UT-072 | Unit | Warehouse | warehouse.dim_companies | SCD2 integrity | No company has multiple current versions | postgresql/warehouse/tests/dim_companies_tests.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026 | S10
UT-073 | Unit | Warehouse | warehouse.dim_companies | Consistency | Current records must not have an effective end date | postgresql/warehouse/tests/dim_companies_tests.sql (TEST 3) | 0 rows | 0 rows | Pass | 30/09/2026 | S10
UT-074 | Unit | Warehouse | warehouse.dim_companies | Consistency | Historical records must have an effective end date | postgresql/warehouse/tests/dim_companies_tests.sql (TEST 4) | count = 0 | 0 | Pass | 30/09/2026 | S10
UT-075 | Unit | Warehouse | warehouse.dim_companies | Consistency | Effective end date must be after start date | postgresql/warehouse/tests/dim_companies_tests.sql (TEST 5) | 0 rows | 0 rows | Pass | 30/09/2026 | S10
UT-076 | Unit | Warehouse | warehouse.dim_companies | Referential integrity | Every source company should exist in the warehouse dimension | postgresql/warehouse/tests/dim_companies_tests.sql (TEST 6) | 0 rows | 0 rows | Pass | 30/09/2026 | S10
UT-077 | Unit | Warehouse | warehouse.dim_companies | Business rule | Warehouse should not contain companies absent from the source | postgresql/warehouse/tests/dim_companies_tests.sql (TEST 7) | 0 rows | 0 rows | Pass | 30/09/2026 | S10
UT-078 | Unit | Warehouse | warehouse.dim_companies | Completeness | Required attributes must not be NULL | postgresql/warehouse/tests/dim_companies_tests.sql (TEST 8) | 0 rows | 0 rows | Pass | 30/09/2026 | S10
UT-079 | Unit | Warehouse | warehouse.dim_companies | Domain / allowed values | Company type must contain only allowed values | postgresql/warehouse/tests/dim_companies_tests.sql (TEST 9) | 0 rows | 0 rows | Pass | 30/09/2026 | S10
UT-080 | Unit | Warehouse | warehouse.dim_companies | Range | Rating must remain between 1.0 and 5.0 | postgresql/warehouse/tests/dim_companies_tests.sql (TEST 10) | 0 rows | 0 rows | Pass | 30/09/2026 | S10
UT-081 | Unit | Warehouse | warehouse.dim_companies | SCD2 integrity | Initial warehouse version starts at source created_at | postgresql/warehouse/tests/dim_companies_tests.sql (TEST 11) | 0 rows (first version of every company starts at created_at) | 0 rows | Pass | 30/09/2026 | S10
UT-082 | Unit | Warehouse | warehouse.dim_customers | Reconciliation | Source vs Warehouse row count | postgresql/warehouse/tests/dim_customers_tests.sql (TEST 1) | source = warehouse | 94,755 = 94,755 | Pass | 30/09/2026
UT-083 | Unit | Warehouse | warehouse.dim_customers | Uniqueness | No duplicate customer_id | postgresql/warehouse/tests/dim_customers_tests.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026
UT-084 | Unit | Warehouse | warehouse.dim_customers | Business rule | One warehouse row per customer | postgresql/warehouse/tests/dim_customers_tests.sql (TEST 3) | rows = distinct customers | 94,755 = 94,755 | Pass | 30/09/2026
UT-085 | Unit | Warehouse | warehouse.dim_customers | Referential integrity | Every source customer exists in warehouse | postgresql/warehouse/tests/dim_customers_tests.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026
UT-086 | Unit | Warehouse | warehouse.dim_customers | Referential integrity | No orphan warehouse customers | postgresql/warehouse/tests/dim_customers_tests.sql (TEST 5) | 0 rows | 0 rows | Pass | 30/09/2026
UT-087 | Unit | Warehouse | warehouse.dim_products | Reconciliation | Source vs Warehouse row count | postgresql/warehouse/tests/dim_products_tests.sql (TEST 1) | source = warehouse | 96 = 96 | Pass | 30/09/2026
UT-088 | Unit | Warehouse | warehouse.dim_products | Uniqueness | No duplicate product_id | postgresql/warehouse/tests/dim_products_tests.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026
UT-089 | Unit | Warehouse | warehouse.dim_products | Referential integrity | Every source product exists in warehouse | postgresql/warehouse/tests/dim_products_tests.sql (TEST 3) | 0 rows | 0 rows | Pass | 30/09/2026
UT-090 | Unit | Warehouse | warehouse.dim_products | Referential integrity | No orphan warehouse products | postgresql/warehouse/tests/dim_products_tests.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026
UT-091 | Unit | Warehouse | warehouse.dim_supplier_product | Reconciliation | Source vs Warehouse row count | postgresql/warehouse/tests/dim_supplier_product_tests.sql (TEST 1) | source = warehouse | 347 = 347 | Pass | 30/09/2026
UT-092 | Unit | Warehouse | warehouse.dim_supplier_product | Uniqueness | No duplicate supplier_product_id | postgresql/warehouse/tests/dim_supplier_product_tests.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026
UT-093 | Unit | Warehouse | warehouse.dim_supplier_product | Referential integrity | Every source mapping exists in warehouse | postgresql/warehouse/tests/dim_supplier_product_tests.sql (TEST 3) | 0 rows | 0 rows | Pass | 30/09/2026
UT-094 | Unit | Warehouse | warehouse.dim_supplier_product | Referential integrity | No orphan warehouse mappings | postgresql/warehouse/tests/dim_supplier_product_tests.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026
UT-095 | Unit | Warehouse | warehouse.dim_supplier_product | Key integrity | supplier_key correctly resolves to warehouse.dim_suppliers | postgresql/warehouse/tests/dim_supplier_product_tests.sql (TEST 5) | 0 rows | 0 rows | Pass | 30/09/2026
UT-096 | Unit | Warehouse | warehouse.dim_supplier_product | Key integrity | product_key correctly resolves to warehouse.dim_products | postgresql/warehouse/tests/dim_supplier_product_tests.sql (TEST 6) | 0 rows | 0 rows | Pass | 30/09/2026
UT-097 | Unit | Warehouse | warehouse.dim_supplier_product | Range | supplier_price and lead_time_days must be non-negative | postgresql/warehouse/tests/dim_supplier_product_tests.sql (TEST 7) | 0 rows | 0 rows | Pass | 30/09/2026
UT-098 | Unit | Warehouse | warehouse.dim_supplier_product | Reconciliation | Warehouse attributes match intermediate (catches stale rows) | postgresql/warehouse/tests/dim_supplier_product_tests.sql (TEST 8) | 0 rows | 0 rows | Pass | 30/09/2026
UT-099 | Unit | Warehouse | warehouse.dim_supplier_product | Business rule | Idempotency check | postgresql/warehouse/tests/dim_supplier_product_tests.sql (TEST 9) | count unchanged after re-run | 351 | Pass | 30/09/2026
UT-100 | Unit | Warehouse | warehouse.dim_suppliers | Reconciliation | Source vs Warehouse row count | postgresql/warehouse/tests/dim_suppliers_tests.sql (TEST 1) | source = warehouse | 400 = 400 | Pass | 30/09/2026
UT-101 | Unit | Warehouse | warehouse.dim_suppliers | Uniqueness | No duplicate supplier_id | postgresql/warehouse/tests/dim_suppliers_tests.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026
UT-102 | Unit | Warehouse | warehouse.dim_suppliers | Business rule | One warehouse row per supplier | postgresql/warehouse/tests/dim_suppliers_tests.sql (TEST 3) | rows = distinct suppliers | 400 = 400 | Pass | 30/09/2026
UT-103 | Unit | Warehouse | warehouse.dim_suppliers | Referential integrity | Every source supplier exists in warehouse | postgresql/warehouse/tests/dim_suppliers_tests.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026
UT-104 | Unit | Warehouse | warehouse.dim_suppliers | Referential integrity | No orphan warehouse suppliers | postgresql/warehouse/tests/dim_suppliers_tests.sql (TEST 5) | 0 rows | 0 rows | Pass | 30/09/2026
UT-105 | Unit | Warehouse | warehouse.fact_leads | Reconciliation | Source vs warehouse row count | postgresql/warehouse/tests/fact_leads_tests.sql (TEST 1) | intermediate = warehouse | 148,358 = 148,358 | Pass | 30/09/2026
UT-106 | Unit | Warehouse | warehouse.fact_leads | Uniqueness | Duplicate lead_id | postgresql/warehouse/tests/fact_leads_tests.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026
UT-107 | Unit | Warehouse | warehouse.fact_leads | Consistency | Every lead has a valid date_key | postgresql/warehouse/tests/fact_leads_tests.sql (TEST 3) | 0 rows | 0 rows | Pass | 30/09/2026
UT-108 | Unit | Warehouse | warehouse.fact_leads | Consistency | date_key correctly represents lead created_at | postgresql/warehouse/tests/fact_leads_tests.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026
UT-109 | Unit | Warehouse | warehouse.fact_leads | Referential integrity | Every populated order_id must exist in orders | postgresql/warehouse/tests/fact_leads_tests.sql (TEST 5) | 0 rows | 0 rows | Pass | 30/09/2026
UT-110 | Unit | Warehouse | warehouse.fact_leads | Reconciliation | Lead-to-order relationship matches intermediate | postgresql/warehouse/tests/fact_leads_tests.sql (TEST 6) | 0 rows | 0 rows | Pass | 30/09/2026
UT-111 | Unit | Warehouse | warehouse.fact_leads | Range | Lead score must be within valid range | postgresql/warehouse/tests/fact_leads_tests.sql (TEST 7) | 0 rows | 0 rows | Pass | 30/09/2026
UT-112 | Unit | Warehouse | warehouse.fact_leads | Business rule | Idempotency | postgresql/warehouse/tests/fact_leads_tests.sql (TEST 8) | count unchanged after re-run | 148,358 | Pass | 30/09/2026
UT-113 | Unit | Warehouse | warehouse.fact_order_items | Reconciliation | Warehouse row count vs intermediate | postgresql/warehouse/tests/fact_order_items_tests.sql (TEST 1) | intermediate = warehouse | 470,263 = 470,263 | Pass | 30/09/2026
UT-114 | Unit | Warehouse | warehouse.fact_order_items | Uniqueness | Duplicate order items | postgresql/warehouse/tests/fact_order_items_tests.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026
UT-115 | Unit | Warehouse | warehouse.fact_order_items | Consistency | Every fact order item has a valid date_key | postgresql/warehouse/tests/fact_order_items_tests.sql (TEST 3) | 0 rows | 0 rows | Pass | 30/09/2026
UT-116 | Unit | Warehouse | warehouse.fact_order_items | Business rule | Every order item maps to a valid customer | postgresql/warehouse/tests/fact_order_items_tests.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026
UT-117 | Unit | Warehouse | warehouse.fact_order_items | Business rule | Every order item maps to a valid product | postgresql/warehouse/tests/fact_order_items_tests.sql (TEST 5) | 0 rows | 0 rows | Pass | 30/09/2026
UT-118 | Unit | Warehouse | warehouse.fact_order_items | Business rule | Every order item resolves to a valid supplier | postgresql/warehouse/tests/fact_order_items_tests.sql (TEST 6) | 0 rows | 0 rows | Pass | 30/09/2026
UT-119 | Unit | Warehouse | warehouse.fact_order_items | Business rule | Every order item maps to a valid company | postgresql/warehouse/tests/fact_order_items_tests.sql (TEST 7) | 0 rows | 0 rows | Pass | 30/09/2026
UT-120 | Unit | Warehouse | warehouse.fact_order_items | Business rule | Quantity must be positive | postgresql/warehouse/tests/fact_order_items_tests.sql (TEST 8) | 0 rows | 0 rows | Pass | 30/09/2026
UT-121 | Unit | Warehouse | warehouse.fact_order_items | Range | Unit price must not be negative | postgresql/warehouse/tests/fact_order_items_tests.sql (TEST 9) | 0 rows | 0 rows | Pass | 30/09/2026
UT-122 | Unit | Warehouse | warehouse.fact_order_items | Range | Discount amount must not be negative | postgresql/warehouse/tests/fact_order_items_tests.sql (TEST 10) | 0 rows | 0 rows | Pass | 30/09/2026
UT-123 | Unit | Warehouse | warehouse.fact_order_items | Range | Line total must not be negative | postgresql/warehouse/tests/fact_order_items_tests.sql (TEST 11) | 0 rows | 0 rows | Pass | 30/09/2026
UT-124 | Unit | Warehouse | warehouse.fact_order_items | Reconciliation | Line total should equal quantity × unit price | postgresql/warehouse/tests/fact_order_items_tests.sql (TEST 12) | 0 rows | 0 rows | Pass | 30/09/2026
UT-125 | Unit | Warehouse | warehouse.fact_order_items | Referential integrity | Every order item belongs to an existing order | postgresql/warehouse/tests/fact_order_items_tests.sql (TEST 13) | 0 rows | 0 rows | Pass | 30/09/2026
UT-126 | Unit | Warehouse | warehouse.fact_order_items | Business rule | Every order has at least one order item | postgresql/warehouse/tests/fact_order_items_tests.sql (TEST 14) | 0 rows | 0 rows | Pass | 30/09/2026
UT-127 | Unit | Warehouse | warehouse.fact_order_items | Business rule | Idempotency check | postgresql/warehouse/tests/fact_order_items_tests.sql (TEST 15) | count unchanged after re-run | 470,263 | Pass | 30/09/2026
UT-128 | Unit | Warehouse | warehouse.fact_orders | Reconciliation | Fact row count matches intermediate orders | postgresql/warehouse/tests/fact_orders_tests.sql (TEST 1) | intermediate = warehouse | 156,678 = 156,678 | Pass | 30/09/2026
UT-129 | Unit | Warehouse | warehouse.fact_orders | Uniqueness | No duplicate fact orders | postgresql/warehouse/tests/fact_orders_tests.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026
UT-130 | Unit | Warehouse | warehouse.fact_orders | Consistency | Every fact order has a valid date_key | postgresql/warehouse/tests/fact_orders_tests.sql (TEST 3) | 0 rows | 0 rows | Pass | 30/09/2026
UT-131 | Unit | Warehouse | warehouse.fact_orders | Key integrity | Every fact order has a valid customer_key | postgresql/warehouse/tests/fact_orders_tests.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026
UT-132 | Unit | Warehouse | warehouse.fact_orders | Key integrity | Every fact order has a valid company_key | postgresql/warehouse/tests/fact_orders_tests.sql (TEST 5) | 0 rows | 0 rows | Pass | 30/09/2026
UT-133 | Unit | Warehouse | warehouse.fact_orders | Business rule | Every order contains at least one order item | postgresql/warehouse/tests/fact_orders_tests.sql (TEST 6) | 0 rows | 0 rows | Pass | 30/09/2026
UT-134 | Unit | Warehouse | warehouse.fact_orders | Reconciliation | item_count matches intermediate.order_items | postgresql/warehouse/tests/fact_orders_tests.sql (TEST 7) | 0 rows | 0 rows | Pass | 30/09/2026
UT-135 | Unit | Warehouse | warehouse.fact_orders | Range | order_total cannot be negative | postgresql/warehouse/tests/fact_orders_tests.sql (TEST 8) | 0 rows | 0 rows | Pass | 30/09/2026
UT-136 | Unit | Warehouse | warehouse.fact_orders | Domain / allowed values | Order status contains only allowed values | postgresql/warehouse/tests/fact_orders_tests.sql (TEST 9) | 0 rows | 0 rows | Pass | 30/09/2026
UT-137 | Unit | Warehouse | warehouse.fact_orders | Domain / allowed values | Payment status contains only allowed values | postgresql/warehouse/tests/fact_orders_tests.sql (TEST 10) | 0 rows | 0 rows | Pass | 30/09/2026
UT-138 | Unit | Warehouse | warehouse.fact_orders | Consistency | Fact order date matches date dimension | postgresql/warehouse/tests/fact_orders_tests.sql (TEST 11) | 0 rows | 0 rows | Pass | 30/09/2026
UT-139 | Unit | Warehouse | warehouse.fact_orders | Key integrity | Company surrogate key must represent the correct | postgresql/warehouse/tests/fact_orders_tests.sql (TEST 12) | 0 rows | 0 rows | Pass | 30/09/2026
UT-140 | Unit | Warehouse | warehouse.fact_orders | Business rule | Idempotency check | postgresql/warehouse/tests/fact_orders_tests.sql (TEST 13) | intermediate = warehouse after re-run | 156,678 = 156,678 | Pass | 30/09/2026
UT-141 | Unit | Warehouse | warehouse (all tables) | Uniqueness | Only one current company version | postgresql/warehouse/tests/fact_warehouse_tests.sql (TEST 1) | 0 rows | 0 rows | Pass | 30/09/2026 | S8
UT-142 | Unit | Warehouse | warehouse (all tables) | Consistency | Company effective dates are valid | postgresql/warehouse/tests/fact_warehouse_tests.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026 | S8
UT-143 | Unit | Warehouse | warehouse (all tables) | Referential integrity | Orders → Customers | postgresql/warehouse/tests/fact_warehouse_tests.sql (TEST 3A) | 0 rows | 0 rows | Pass | 30/09/2026 | S8
UT-144 | Unit | Warehouse | warehouse (all tables) | Referential integrity | Orders → Companies | postgresql/warehouse/tests/fact_warehouse_tests.sql (TEST 3B) | 0 rows | 0 rows | Pass | 30/09/2026 | S8
UT-145 | Unit | Warehouse | warehouse (all tables) | Referential integrity | Order Items → Products | postgresql/warehouse/tests/fact_warehouse_tests.sql (TEST 3C) | 0 rows | 0 rows | Pass | 30/09/2026 | S8
UT-146 | Unit | Warehouse | warehouse (all tables) | Referential integrity | Order Items → Suppliers | postgresql/warehouse/tests/fact_warehouse_tests.sql (TEST 3D) | 0 rows | 0 rows | Pass | 30/09/2026 | S8
UT-147 | Unit | Warehouse | warehouse (all tables) | Referential integrity | Web Logs → Date | postgresql/warehouse/tests/fact_warehouse_tests.sql (TEST 3E) | 0 rows | 0 rows | Pass | 30/09/2026 | S8
UT-148 | Unit | Warehouse | warehouse (all tables) | Referential integrity | Leads → Date | postgresql/warehouse/tests/fact_warehouse_tests.sql (TEST 3F) | 0 rows | 0 rows | Pass | 30/09/2026 | S8
UT-149 | Unit | Warehouse | warehouse (all tables) | Business rule | Every order has at least one order item | postgresql/warehouse/tests/fact_warehouse_tests.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026 | S8
UT-150 | Unit | Warehouse | warehouse (all tables) | Reconciliation | item_count matches actual order items | postgresql/warehouse/tests/fact_warehouse_tests.sql (TEST 5) | 0 rows | 0 rows | Pass | 30/09/2026 | S8
UT-151 | Unit | Warehouse | warehouse.fact_web_logs | Reconciliation | Source vs warehouse row count | postgresql/warehouse/tests/fact_web_logs_tests.sql (TEST 1) | intermediate = warehouse | 296,703 = 296,703 | Pass | 30/09/2026
UT-152 | Unit | Warehouse | warehouse.fact_web_logs | Uniqueness | Duplicate log_id | postgresql/warehouse/tests/fact_web_logs_tests.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026
UT-153 | Unit | Warehouse | warehouse.fact_web_logs | Consistency | Every log has a valid date_key | postgresql/warehouse/tests/fact_web_logs_tests.sql (TEST 3) | 0 rows | 0 rows | Pass | 30/09/2026
UT-154 | Unit | Warehouse | warehouse.fact_web_logs | Consistency | Every log timestamp maps to the correct date_key | postgresql/warehouse/tests/fact_web_logs_tests.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026
UT-155 | Unit | Warehouse | warehouse.fact_web_logs | Domain / allowed values | HTTP status codes must be valid | postgresql/warehouse/tests/fact_web_logs_tests.sql (TEST 5) | 0 rows | 0 rows | Pass | 30/09/2026
UT-156 | Unit | Warehouse | warehouse.fact_web_logs | Range | bytes_sent cannot be negative | postgresql/warehouse/tests/fact_web_logs_tests.sql (TEST 6) | 0 rows | 0 rows | Pass | 30/09/2026
UT-157 | Unit | Warehouse | warehouse.fact_web_logs | Business rule | Idempotency | postgresql/warehouse/tests/fact_web_logs_tests.sql (TEST 7) | count unchanged after re-run | 296,703 | Pass | 30/09/2026
UT-158 | Unit | Intermediate | intermediate.rejected_records | Completeness | Quarantine is not empty for either CSV table | postgresql/intermediate/tests/Test_rejected_records.sql (TEST 1) | 0 rows | 0 rows | Pass | 30/09/2026
UT-159 | Unit | Intermediate | intermediate.rejected_records | Uniqueness | No duplicate rejected records | postgresql/intermediate/tests/Test_rejected_records.sql (TEST 2) | 0 rows | 0 rows | Pass | 30/09/2026
UT-160 | Unit | Intermediate | intermediate.rejected_records | Domain / allowed values | Only CSV tables and known reject reasons | postgresql/intermediate/tests/Test_rejected_records.sql (TEST 3) | 0 rows | 0 rows | Pass | 30/09/2026
UT-161 | Unit | Intermediate | intermediate.rejected_records | Range | Rejected share between 0.5% and 3% (about 1.5% expected) | postgresql/intermediate/tests/Test_rejected_records.sql (TEST 4) | 0 rows | 0 rows | Pass | 30/09/2026

## Integration_Tests
Test ID | Level | Layer | Object Under Test | Test Type | Description | Test Script / File | Expected Result | Actual Result | Status | Executed On | Evidence | Defect ID
IT-01 | Integration | Source, Intermediate | Source -> intermediate completeness | Cross-layer reconciliation | Every source record (8 tables + 2 files) is in intermediate or in rejected_records | postgresql/tests/integration_tests.sql (IT-01, manual count) | Every source record (8 tables + 2 files) is in intermediate or in rejected_records | 0 differences (2,258 + 4,517 rejected CSV rows) | Pass | 30/09/2026
IT-02 | Integration | Staging, Intermediate | Staging cleared after a successful run | Cross-layer reconciliation | Every staging row is in intermediate or rejected_records; then all 10 staging tables are empty | postgresql/tests/integration_tests.sql (IT-02) | 0 staging rows after the run | 0 staging rows left | Pass | 30/09/2026
IT-03 | Integration | Intermediate, Warehouse | Intermediate -> warehouse completeness | Cross-layer reconciliation | Row counts equal for 5 dimensions (current rows) and 4 facts | postgresql/tests/integration_tests.sql (IT-03) | Row counts equal for 5 dimensions (current rows) and 4 facts | 0 differences | Pass | 30/09/2026 | S9
IT-04 | Integration | Metadata, Source | CDC watermark correctness | Cross-layer reconciliation | Each of the 8 watermarks = MAX(updated_at) of its source table | postgresql/tests/integration_tests.sql (IT-04) | Each of the 8 watermarks = MAX(updated_at) of its source table | 8 of 8 watermarks correct | Pass | 30/09/2026
IT-05 | Integration | Source, Intermediate, Warehouse | SCD Type 2 history after CDC updates | Cross-layer reconciliation | Changed companies have a closed old version whose end = start of the new version; one current version each | postgresql/tests/integration_tests.sql (IT-05) | Changed companies have a closed old version whose end = start of the new version; one current version each | 5 companies with history, 0 gaps/overlaps | Pass | 30/09/2026 | S10
IT-06 | Integration | Warehouse | Point-in-time company lookup | Cross-layer reconciliation | Every order points to the company version valid at order time | postgresql/tests/integration_tests.sql (IT-06) | Every order points to the company version valid at order time | 0 orders outside their version's validity | Pass | 30/09/2026
IT-07 | Integration | Warehouse | Order header vs order lines | Cross-layer reconciliation | fact_orders.order_total = SUM(line_total) and item_count = number of lines | postgresql/tests/integration_tests.sql (IT-07) | fact_orders.order_total = SUM(line_total) and item_count = number of lines | 0 mismatching orders | Pass | 30/09/2026
IT-08 | Integration | Intermediate, Warehouse | Lead to order link (cross-source) | Cross-layer reconciliation | Converted leads carry their order_id; every order's lead_id exists in fact_leads | postgresql/tests/integration_tests.sql (IT-08) | Converted leads carry their order_id; every order's lead_id exists in fact_leads | 0 inconsistent leads, 0 orders with unknown lead | Pass | 30/09/2026
IT-09 | Integration | All | End-to-end incremental run | Cross-layer reconciliation | Latest run of all 5 stages has status 'completed' | postgresql/tests/integration_tests.sql (IT-09) | Latest run of all 5 stages has status 'completed' | 5 of 5 stages completed | Pass | 30/09/2026
IT-10 | Integration | Warehouse | Idempotent re-run of warehouse loads | Cross-layer reconciliation | Re-running the four load_fact_*.sql scripts leaves all fact row counts unchanged | Re-run of load_fact_*.sql (30/09/2026) | Re-running the four load_fact_*.sql scripts leaves all fact row counts unchanged | 0 rows changed by each MERGE; counts and value totals identical (orders 156,678, lines 470,263, web logs 296,703, leads 148,358) | Pass | 30/09/2026 | S11

## KPI_Validation
Test ID | KPI ID | KPI | Validation Method | Query / Source | Expected | Actual | Status | Executed On | Evidence
KV-01 | KPI-01 | Monthly Revenue Trend | Sum of monthly net revenue = non-cancelled line revenue of the same 23 complete months | SELECT SUM(net_revenue) FROM marts.vw_monthly_revenue_trend | 4,400,274,489.23 | 4,400,274,489.23 | Pass | 30/09/2026 | S13
KV-02 | KPI-02 | Revenue by Company | Sum of company gross revenue = SUM(quantity x unit_price) of buyer, non-cancelled lines | SELECT SUM(gross_revenue) FROM marts.vw_revenue_by_company | 5,133,378,828.46 | 5,133,378,828.46 | Pass | 30/09/2026
KV-03 | KPI-03 | Revenue by Product | Sum of product net revenue = total net revenue; one row per product | SELECT SUM(net_revenue) FROM marts.vw_revenue_by_product | 4,621,200,118.84 | 4,621,200,118.84 | Pass | 30/09/2026
KV-04 | KPI-04 | Gross Margin Analysis | Sum of gross profit = SUM(line_total - quantity x supplier_price) | SELECT SUM(gross_profit) FROM marts.vw_gross_margin_analysis | 954,597,910.13 | 954,597,910.13 | Pass | 30/09/2026
KV-05 | KPI-05 | Customer Lifetime Value | Sum of company total spend = net revenue of buyer companies | SELECT SUM(total_spend) FROM marts.vw_customer_lifetime_value | 4,621,200,118.84 | 4,621,200,118.84 | Pass | 30/09/2026
KV-06 | KPI-06 | Customer Activity | Repeat purchase rate recomputed from fact_orders | SELECT MAX(repeat_purchase_rate_pct) FROM marts.vw_customer_activity | 60.31 | 60.31 | Pass | 30/09/2026
KV-07 | KPI-07 | Geographic Sales | Sum of revenue by location = total net revenue | SELECT SUM(revenue_by_location) FROM marts.vw_geographic_sales | 4,621,200,118.84 | 4,621,200,118.84 | Pass | 30/09/2026
KV-08 | KPI-08 | Traffic by Device | Sum of sessions = distinct (session, device) of non-bot requests | SELECT SUM(total_sessions) FROM marts.vw_traffic_by_device | 281,911 | 281,911 | Pass | 30/09/2026
KV-09 | KPI-09 | Geographic Web Traffic | Countries in the view = countries in non-bot web logs | SELECT COUNT(DISTINCT country) FROM marts.vw_geographic_web_traffic | 3 | 3 | Pass | 30/09/2026
KV-10 | KPI-10 | Web Activity Quality | Sum of requests by endpoint = all web-log rows; errors = status 400-599 | SELECT SUM(total_requests)::text ¦¦ ' / ' ¦¦ SUM(error_4xx+error_5xx)::text FROM marts.vw_web_activity_quality | 296703 / 59348 | 296703 / 59348 | Pass | 30/09/2026
KV-11 | KPI-11 | Lead Conversion Funnel | Sum of converted leads = leads with conversion_status 'Converted' | SELECT SUM(converted_leads) FROM marts.vw_lead_conversion_funnel | 6,044 | 6,044 | Pass | 30/09/2026
KV-12 | KPI-12 | Lead Quality vs Order Value | Converted-lead count = independent join count; correlation within -1..1 | SELECT converted_leads::text ¦¦ ' ¦ r=' ¦¦ lead_score_order_value_correlation::text FROM marts.vw_lead_quality_vs_order_value | 5748 ¦ r=0.0071 | 5748 ¦ r=0.0071 | Pass | 30/09/2026
KV-13 | KPI-13 | Supplier Revenue | Sum of supplier revenue = total net revenue; shares add up to 100 % | SELECT SUM(total_revenue)::text ¦¦ ' ¦ ' ¦¦ ROUND(SUM(revenue_share_pct))::text ¦¦ '%' FROM marts.vw_supplier_revenue | 4621200118.84 ¦ 100% | 4621200118.84 ¦ 100% | Pass | 30/09/2026
KV-14 | KPI-14 | Supplier Product Performance | Sum of supplier-product revenue = total net revenue | SELECT SUM(total_revenue) FROM marts.vw_supplier_product_performance | 4,621,200,118.84 | 4,621,200,118.84 | Pass | 30/09/2026
KV-15 | KPI-15 | Pipeline Execution Metrics | One row per pipeline in the run log; data freshness / watermark lag populated | SELECT COUNT(*)::text ¦¦ ' rows, ' ¦¦ COUNT(data_freshness)::text ¦¦ ' with freshness' FROM marts.vw_pipeline_execution_metrics | 5 rows, 5 with freshness | 5 rows, 5 with freshness | Pass | 30/09/2026

## Defect_Log
Defect ID | Test ID | Found In | Description | Severity | Status | Root Cause | Fix / Commit | Closed On
D-01 | UT-046..UT-050 | Test_web_logs.sql | A leftover query at the top returned every web log | Low | Closed | Debug query left in the file | Query removed | 30/09/2026
D-02 | UT-051..UT-062 | Tests_companies.sql | A stray semicolon split one test in two | Low | Closed | Typo | Semicolon removed | 30/09/2026
D-03 | UT-004, UT-005 | Test_categories.sql | Missing semicolon; TEST 5 checked companies instead of categories | Low | Closed | Copy-paste error | Semicolon added; table corrected | 30/09/2026
D-04 | UT-081 | dim_companies_tests.sql (TEST 11) | Checked the current SCD2 version instead of the first one; failed after a company change | Medium | Closed | Wrong version compared | Compare MIN(effective_start_date) per company | 30/09/2026
D-05 | KV-06 | marts.vw_customer_activity (KPI 6) | 449 customers without a country | Medium | Closed | Extra is_current filter on an as-of key | Join on company_key only | 30/09/2026
D-06 | KV-01 | marts.vw_monthly_revenue_trend (KPI 1) | Future and partial months included; 'Latest Net MoM %' card showed '--' | Medium | Closed | dim_date runs 6 months ahead | Complete months only; month_num / month_start added | 30/09/2026
D-07 | - | Data generators | Daily data back-dated; volume ramp hid seasonality; no failed/refunded payments | High | Closed | Customer picked before the order date | Date first, then customer; daily data dated today; payment by order status | 30/09/2026